|  |  |
| --- | --- |
| **Project** | Rice variety evaluation |
| **Project name** |  |
| **Year of record** | 2023 |
| **Q 1** | Output 1 - Milestone 1 Activity 1 - Observational trial of 62 rice varieties on paddy condition - 100% completed and in progress into flowering stages now Activity 2 - Micro plot trial of 32 rice varieties evaluated on the upland field - Lack of evaluation skills at each evaluation stage Output 2 - Milestone 2 Activity 1 - Detailed variety studies and selected 16-20 rice varieties under upland - Bad weather condition Activity 2 - Detailed variety studies and selected 16-20 rice varieties under irrigated - bad weather conditioin |
| **Q 2** | Output 2 - Milestone 2 Activity 2.1 - Detailed variety studies and selected 16-20 rice varieties under upland - Bad weather condition Activity 2.2 - Detailed variety studies and selected 11 rice varieties under irrigated - Bad weather condition |
| **Q 3** | Output 3. Selection of best accessions from Macro plot trials Trial established with 8 selected accessions; data collected and some varieties reaching heading stage; |
| **Q 4** |  |