NARI Quarterly Milestone Report

Project Name	Growth response of pathogen-tested sweetpotato cultivars to Nitrogen application methods in highlands agro-ecological zones of Papua New Guinea.
Project Number	APSF 23022 (A10237)
Project Leader	William Sirabis
Implementing NARI Centres	Highlands Regional Centre
Reporting period	July 31 – September 30, 2023
Date report completed	October 10, 2023

Progress towards achievement of the milestones set for the period
Progression of set milestones of the reporting period are outlined in the accompanying	document 2023_Q3Report_APSF.ods; tab name Quarterly_report –	Period	milestones
Progress towards the achievement of the planned outputs and Strategic Objective
Progression in achieving the planned outputs and strategic objectives are outlined in the accompanying document – 2023_Q3Report_APSF.ods; tab name Quarterly_report – Planned output & strategic obj.
Explanation as to significant variances from timelines and implementation plans

- Due to technical issues affecting NARI email/ internet services the primary email sent to APSF did not reach them. This had to be recent to facilitate first instalment of project funds, which was intended for July 01. Subsequently, this fund was not cleared as soon as anticipated due to the inefficient upgrade of BSP banking services since April 2023. Funds were transferred to the NARI Aiyura Account in early September
- The above mentioned has affected setting of the Pot Trial proposed for August. Additionally, the replacement of skylight roofing in the nursery, as well as the lack of working space in the nursery has further put a hold on the activity. There is now sufficient space to start the experiment, after the PGR/ crop breeding team have moved their potted sweet potato plants to the newly erected nursery in Green Compound.
- Field activities have not been entirely affected, as the initial phase is a pre-trial corn cover crop to attempt run down soil fertility to illuminate treatment effects
Modifications in the implementation plan impending problems and recommended solutions

Milestone dates for the Pot trial have been moved back by 2-3 months
Lessons learnt or any other relevant observations as part of implementation

If possible, in cases of urgency to carryout project activities, in agreement with on-site management, alternative funds can be used to finance activities, and funds be reimbursed as soon as it is made available.

6. Provide a financial report for the 6 month period showing planned and actual expenditure per budget line.

Quarter 2 Financial Report
Item No	Item description	Planned Expenditure, PGK	Actual expenditure, PGK	Remarks
1	Travel	1250	-	-
2	Labour charge	250	-	-
3	Project materials	700	-	-
4	-	-	-	-
		Total expenditure, PGK	-

Balance in Aiyura accounts is PGK 14 000.00 as of 05.09.2023
Last transfer of project funds from HQ, 05.09.2023 – PGK 14 000.00. Actual expenditure has yet to be capture in the accounts cash flow analysis.

Please provide copies of any relevant reports or other information completed during this reporting period as separate attachments when you submit your report

No relevant reports have been produced in the period.